## Sheet1
ID | Title | User Story | Role | Category | Priority | Acceptance Criteria | STATUS
PB1 | User Signup | As a user, I want to sign up so that I can start shopping. | User | Authentication | High | Form validation, email/phone verification | TO DO
PB2 | User Login/Logout | As a user, I want to log in and log out securely so that my account is protected. | User | Authentication | High | Valid credentials, session timeout, logout clears session | TO DO
PB3 | Search Products | As a user, I want to search for products so that I can find what I need. | User | Catalog | High | Keyword search, filters, sort options | TO DO
PB4 | Add to Cart | As a user, I want to add products to my cart so that I can buy them later. | User | Cart | High | Add button, quantity selector, confirmation | TO DO
PB5 | Remove from Cart | As a user, I want to remove items from my cart so that I can update my purchase list. | User | Cart | High | Remove button, instant update | TO DO
PB6 | Checkout Cart | As a user, I want to checkout so that I can place an order. | User | Checkout | High | Address selection, payment, confirmation | TO DO
PB7 | View Order Status | As a user, I want to track my order so that I know when it will arrive. | User | Orders | Medium | Real-time status, tracking ID | TO DO
PB8 | Cancel Order | As a user, I want to cancel an order so that I can change my mind. | User | Orders | Medium | Cancel button, confirmation, refund trigger | TO DO
PB9 | View Order History | As a user, I want to see my past orders so that I can track purchases. | User | Orders | Medium | List of orders, filter by date/status | TO DO
PB10 | Manage Reviews | As a user, I want to add, edit, and remove reviews so that I can share feedback. | User | Reviews | Medium | Rating + comment, edit/delete options | TO DO
PB11 | View Notifications | As a user, I want to view notifications so that I stay updated. | User | Communication | Medium | Notification center, order updates, offers | TO DO
PB12 | Manage Profile | As a user, I want to update my profile so that my shipping info is accurate. | User | Profile | Medium | Edit name, address, phone, password | TO DO
PB13 | Empty Cart | As a user, I want to clear my cart so that I can start fresh. | User | Cart | Low | "Empty Cart" button, confirmation prompt | TO DO
PB14 | Merchant Signup | As a merchant, I want to sign up so that I can start selling products. | Merchant | Authentication | High | Form validation, email/phone verification | TO DO
PB15 | Merchant Login/Logout | As a merchant, I want to log in and log out securely so that I can manage my store. | Merchant | Authentication | High | Valid credentials, session timeout, logout clears session | TO DO
PB16 | Manage Products | As a merchant, I want to add, edit, and remove products so that my catalog is up to date. | Merchant | Product Management | High | Product form, image upload, edit/delete options | TO DO
PB17 | View Orders | As a merchant, I want to view incoming orders so that I can fulfill them promptly. | Merchant | Orders | High | View list, filter by status/date, order details | TO DO
PB18 | Ship Orders | As a merchant, I want to ship orders so that customers receive their products. | Merchant | Fulfillment | High | Update shipping status, assign delivery partner | TO DO
PB19 | View Analytics | As a merchant, I want to view analytics so that I can track performance. | Merchant | Analytics | Medium | Dashboard with sales, top products, trends | TO DO
PB20 | Manage Delivery Options | As a merchant, I want to choose delivery partners or self-ship so that I have flexibility. | Merchant | Logistics | Medium | Select method, assign partner, update status | TO DO
PB21 | Manage Profile | As a merchant, I want to view and update my profile so that my business info is accurate. | Merchant | Profile | Medium | Edit business name, address, bank details | TO DO
PB22 | Admin Login/Logout | As an admin, I want to securely log in and log out so that I can manage the platform safely. | Admin | Authentication | High | Valid credentials, session timeout, logout clears session | TO DO
PB23 | Manage Merchants | As an admin, I want to manage merchant accounts so that I can approve or suspend sellers. | Admin | Merchant Management | High | View list, approve/reject, suspend/reactivate | TO DO
PB24 | Manage Orders | As an admin, I want to view and manage all orders so that I can ensure smooth operations. | Admin | Order Management | High | View orders, filter, update status, assign delivery | TO DO
PB25 | Manage Payments | As an admin, I want to manage payments and disputes so that transactions are secure. | Admin | Payment Management | High | View transactions, resolve disputes, refund processing | TO DO
PB26 | Manage Returns & Refunds | As an admin, I want to handle returns and refunds so that users are satisfied. | Admin | Returns | High | View requests, approve/reject, process refund | TO DO
PB27 | Manage Brands | As an admin, I want to add, edit, and remove brands so that I can organize products effectively. | Admin | Brand Management | High | CRUD operations, validation, confirmation messages | TO DO
PB28 | Manage Categories | As an admin, I want to manage categories so that users can browse products easily. | Admin | Category Management | High | Add/edit/delete categories, nested support | TO DO
PB29 | Manage Features | As an admin, I want to manage product features so that merchants can tag items accurately. | Admin | Feature Management | Medium | Add/edit/delete features, searchable tags | TO DO
PB30 | Manage Reviews | As an admin, I want to moderate reviews so that content remains appropriate. | Admin | Reviews | Medium | View/edit/delete reviews, flag abuse | TO DO
PB31 | Manage Delivery Partners | As an admin, I want to manage delivery partners so that logistics are efficient. | Admin | Logistics | Medium | Add/edit/remove partners, assign to orders | TO DO
PB32 | Send Notifications | As an admin, I want to send notifications to users and merchants so that they stay informed. | Admin | Communication | Medium | Compose message, select recipients, send via email/SMS | TO DO